## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | USER ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATED DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Developer | Understand the problem | I can search for relevant solutions | 1
1 | SB1/US2 | Developer | Understand user stories | I can search for dataset accordingly | 1
1 | SB1/US3 | User | Set object to write | I can set the object | 1
| SB1/US4 | User | Save the object data locally | I don’t have to set object each time
1 | SB1/US5 | User | Change the object | I can change the writing object | 1
2 | SB2/US1 | User | Write on the screen without physical interaction | I can write on the screens | 2
2 | SB2/US2 | Developer | Trace the object user using to write | I can get the signature on the screen | 2
2 | SB2/US3 | Developer | Save the sign into folder | Signature will be saved | 2
2 | SB2/US5 | User | Retry | I can try again if my previous signature is wrong | 3
3 | SB3/US1 | Developer | Find datasets | I can use it | 3
3 | SB3/US2 | Developer | Download datasets from various sources | I can train model on it | 3
3 | SB3/US3 | Developer | Normalize and stem data | I can simplify my dataset | 3
3 | SB3/US4 | Developer | Train different ML models on standard dataset | I can test it's accuracy and performance on each algorithm | 3
3 | SB3/US5 | Developer | Train different DL models on standard dataset | I can test it's accuracy and performance on each algorithm | 3
3 | SB3/US6 | Developer | Train different ML models on my dataset | I can test it's accuracy and performance on each algorithm | 3
3 | SB3/US7 | Developer | Train different DL models on my dataset | I can test it's accuracy and performance on each algorithm | 3
4 | SB4/US1 | Developer | Choose most accurate algorithm | I can implement that and get best results
4 | SB4/US2 | Developer | Improve the input | I can improve the model | 4
4 | SB4/US3 | Developer | Apply my trained model on user stories | Application can be used | 4
4 | SB4/US4 | Developer | Improve the model | Accuracy of the model will be improved | 4
4 | SB4/US5 | Developer | Implement the final model for general user | Application can be used by general user | 4

## SB1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Signature authentication in Air>
SB1/US1 | Understand the problem | SB1/D1/T1 | Breaking the problem and understanding each component | AS+AK+LC | COMPLETED
|  | SB1/D1/T2 | Searching for relavent solutions | AS+AK+LC | COMPLETED
|  | SB1/D1/T3 | Searching alternative approches | AS+AK+LC | COMPLETED
|  | SB1/D1/T4 | Analysing similar projects | AS+AK+LC | COMPLETED
SB1/US2 | Understand user stories | SB1/D2/T1 | Looking for various use cases | AS+AK+LC | COMPLETED
|  | SB1/D2/T2 | Discussion about user stories | AS+AK+LC | COMPLETED
|  | SB1/D2/T3 | Searching for type of data required | AS+AK+LC | COMPLETED
SB1/US3 | Set object to write | SB1/D3/T1 | Set the object constraints | AK | COMPLETED
|  | SB1/D3/T2 | Set the object color | AS+AK+LC | COMPLETED
|  | SB1/D3/T3 | Set HSV values | LC | COMPLETED
SB1/US4 | Save the object data locally | SB1/D4/T1 | Save the constraints of object | AS+AK+LC | COMPLETED
|  | SB1/D4/T2 | Save data in pickle | AS+AK+LC | COMPLETED
|  | SB1/D4/T3 | Load data from pickle | AS | COMPLETED
SB1/US5 | Change the object | SB1/D5/T1 | Change the object constraints | AS | COMPLETED
|  | SB1/D5/T2 | Save the constraints of changed object data | AS | COMPLETED

## SB HOURS 1
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Understand the problem | Breaking the problem and understanding each component | AS+AK+LC | COMPLETED | 5
|  | Searching for relavent solutions | AS+AK+LC | COMPLETED | 12
|  | Searching alternative approches | AS+AK+LC | COMPLETED | 14
|  | Analysing similar projects | AS+AK+LC | COMPLETED | 10
2 | Understand user stories | Looking for various use cases | AS+AK+LC | COMPLETED | 4
|  | Discussion about user stories | AS+AK+LC | COMPLETED | 2
|  | Searching for type of data required | AS+AK+LC | COMPLETED | 2
3 | Set object to write | Set the object constraints | AK | COMPLETED | 2
|  | Set the object color | AS+AK+LC | COMPLETED | 1
|  | Set HSV values | LC | COMPLETED | 1
4 | Save the data object locally | Save the constraints of object | AS+AK+LC | COMPLETED | 10
|  | Save Data in pickle | AS+AK+LC | COMPLETED | 11
|  | load data from pickle | AS | COMPLETED | 4
5 | Change the object | Change the object constraints | AS | COMPLETED | 1
|  | Save the constraints of changed object data | AS | COMPLETED | 1
| AS | Abhishek Sharma
| AK | Ankit Kumawat
| LC | Lokesh Choudhary
Verified By:
(Product Owner)

## SB BD 1
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 15 | 15 | Tasks
2018-09-11 | 11 | 13
2018-09-12 | 8 | 10
2018-09-14 | 5 | 8
2018-09-16 | 2 | 4
2018-09-18 | 0 | 0
Days

## SB2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Signature authentication in Air>
SB2/US1 | Write on the screen without physical interaction | SB2/D1/T1 | Open the Webcam | AS+AK+LC | COMPLETED
|  | SB2/D1/T2 | Write in front of the Camera | AS+AK+LC | COMPLETED
|  | SB2/D1/T3 | Add Validations | AS+AK+LC | COMPLETED
|  | SB2/D1/T4 | Store the data | AS+AK+LC | COMPLETED
SB2/US2 | Trace the object | SB2/D2/T1 | Trace the object on screen | AS+AK+LC | COMPLETED
|  | SB2/D2/T2 | Convert B&W image | AS+AK+LC | COMPLETED
|  | SB2/D2/T3 | Save the Data | AS+AK+LC | COMPLETED
SB2/US3 | Save the sign into folder | SB2/D3/T1 | Create a folder to store | AS+AK+LC | COMPLETED
|  | SB2/D3/T2 | Save the Data in that folder | AS+AK+LC | COMPLETED
SB2/US4 | Retry | SB2/D5/T1 | Again try different sign | AS+AK+LC | COMPLETED
|  | SB2/D5/T2 | Save the data | AS+AK+LC | COMPLETED

## SB HOURS 2
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Write on the screen without physical interaction | Open the Webcam | AS+AK+LC | COMPLETED | 1
|  | Write front of the Camera | AS+AK+LC | COMPLETED | 10
|  | Add Validations | AS+AK+LC | COMPLETED | 1
|  | Store the data of application form | AS+AK+LC | COMPLETED | 5
2 | Trace the object | Trace the object on screen | AS+AK+LC | COMPLETED | 2
|  | Convert B&W image | AS+AK+LC | COMPLETED | 1
|  | Save the Data | AS+AK+LC | COMPLETED | 1
3 | Save the sign into folder | Create a folder to store | AS+AK+LC | COMPLETED | 2
|  | Save the Data in that folder | AS+AK+LC | COMPLETED | 1
4 | Retry | Again try different sign | AS+AK+LC | COMPLETED | 1
|  | Save the data |  | COMPLETED | 1
| AS | Abhishek Sharma
| AK | Ankit Kumawat
| LC | Lokesh Choudhary
Verified By:
(Product Owner)

## SB BD 2
Spring Backlog 2 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-25 | 11 | 11 | Tasks
2018-09-28 | 9 | 10
2018-10-02 | 6 | 8
2018-10-05 | 3 | 5
2018-10-07 | 2 | 3
2018-10-09 | 0 | 0
Days

## SB3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Signature authentication in Air>
SB3/US1 | Find datasets | SB3/D1/T1 | Find the data set from different sources | AS+AK+LC | COMPLETED
|  | SB3/D1/T2 | Select relavent data set | AS+AK+LC | COMPLETED
SB3/US2 | Download datasets from various sources | SB3/D2/T1 | Download datasets Github | AS | COMPLETED
|  | SB3/D2/T2 | Download datasets kaggle | LC | COMPLETED
|  | SB3/D2/T3 | Other Sources | AK | COMPLETED
SB3/US3 | Normalize and set the data | SB3/D3/T1 | Normalize the data | AS+AK+LC | COMPLETED
|  | SB3/D3/T2 | Set the data | AS+AK+LC | COMPLETED
SB3/US4 | Train different ML models on standard dataset | SB3/D4/T1 | Apply ML models on Standard DataSet | AS+AK+LC | IN PROGRESS
|  | SB3/D4/T2 | Store result | AS+AK+LC | IN PROGRESS
SB3/US5 | Train different DL models on standard dataset | SB3/D4/T1 | Apply different DL models on Standard DataSet | AS+AK+LC | IN PROGRESS
|  | SB3/D4/T2 | Store result | AS+AK+LC | IN PROGRESS
SB3/US6 | Train different ML models on my own dataset | SB3/D4/T1 | Apply ML models on my own dataset | AS+AK+LC | IN PROGRESS
|  | SB3/D4/T2 | Store result | AS+AK+LC | IN PROGRESS
SB3/US7 | Train different DL models on my own dataset | SB3/D4/T1 | Apply different DL models on my own dataset | AS+AK+LC | IN PROGRESS
|  | SB3/D4/T2 | Store result | AS+AK+LC | IN PROGRESS

## SB HOURS 3
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Find datasets | Find the data set from different sources | AS+AK+LC |  | 2
|  | Select relavent data set | AS+AK+LC |  | 2
2 | Download datasets from various sources | Download datasets Github | AS |  | 1
|  | Download datasets kaggle | LC |  | 2
|  | Other Sources | AK |  | 2
3 | Normalize and set the data | Normalize the data | AS+AK+LC |  | 3
|  | Set the data | AS+AK+LC |  | 1
4 | Train different ML models on standard dataset | Apply ML models on Standard DataSet | AS+AK+LC |  | 4
|  | Store result | AS+AK+LC |  | 3
5 | Train different DL models on standard dataset | Apply different DL models on Standard DataSet | AS+AK+LC |  | 3
|  | Store result | AS+AK+LC |  | 3
6 | Train different ML models on my dataset | Apply ML models on my dataset | AS+AK+LC |  | 2
|  | Store result | AS+AK+LC |  | 2
7 | Train different DL models on my dataset | Apply different DL models on mt dataset | AS+AK+LC |  | 2
|  | Store result | AS+AK+LC |  | 2
| AS | Abhishek Sharma
| AK | Ankit Kumawat
| LC | Lokesh Choudhary
Verified By:
(Product Owner)

## SB BD 3
Spring Backlog 3 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-10-16 | 15 | 15 | Tasks
2018-10-18 | 13 | 14
2018-10-20 | 10 | 11
2018-10-21 | 8 | 9
2018-10-22 | 6 | 7
2018-10-23 | 0 | 7
Days

## SB4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Signature authentication in Air>
SB4/US1 | Choose most accurate algorithm | SB4/D1/T1 | Compare all the ML models | AS+AK+LC | NOT STARTED
|  | SB4/D1/T2 | Choice best efficient model | AS+AK+LC | NOT STARTED
|  | SB4/D1/T3 | Apply dataset on efficient model | AS+AK+LC | NOT STARTED
|  | SB4/D1/T4 | Check accuracy | AS+AK+LC | NOT STARTED
SB4/US2 | Improve the input | SB4/D2/T1 | Change the dataset and model | AS+AK+LC | NOT STARTED
|  | SB4/D2/T2 | Check accuracy | AS+AK+LC | NOT STARTED
SB4/US3 | Apply my trained model on user stories | SB4/D3/T1 | Apply my trained model on user stories | AS+AK+LC | NOT STARTED
|  | SB4/D3/T2 | Check model status | AS+AK+LC | NOT STARTED
SB4/US4 | Improve the model | SB4/D4/T1 | Improve the model with more accurate data | AS+AK+LC | NOT STARTED
SB4/US5 | Implement the final model for general user | SB4/D5/T1 | Implement the model for all the users | AS+AK+LC | NOT STARTED

## SB HOURS 4
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Choose most accurate algorithm | Compare all the ML models | AS+AK+LC |  | 2
|  | Choice best efficient model | AS+AK+LC |  | 2
|  | Apply dataset on efficient model | AS+AK+LC |  | 3
|  | Check accuracy | AS+AK+LC |  | 1
2 | Improve the input | Change the dataset and model | AS+AK+LC |  | 3
|  | Check accuracy | AS+AK+LC |  | 1
3 | Apply my trained model on user stories | Apply my trained model on user stories | AS+AK+LC |  | 3
|  | Check model status | AS+AK+LC |  | 2
4 | Improve the model | Improve the model with more accurate data | AS+AK+LC |  | 4
5 | Implement the final model for general user | Implement the model for all the users | AS+AK+LC |  | 2
| AS | Abhishek Sharma
| AK | Ankit Kumawat
| LC | Lokesh Choudhary
Verified By:
(Product Owner)

## SB BD 4
Spring Backlog 3 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 10 | 10 | Tasks
2018-09-11 | 6 | 10
2018-09-12 | 4 | 10
2018-09-14 | 3 | 10
2018-09-16 | 2 | 10
2018-09-18 | 0 | 10
Days

## BD
Date | Planned Task | Actual Uncompleted Task
2018-08-06 | 10 | 2
13 Aug. 2018 | 5 | 3
20 Aug. 2018 | 4 | 2
27 Aug. 2018 | 5 | 0
4 Sept. 2018 | 4 | 2
Total | 28 | 9