## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | USER ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATED DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Developer | Understand the problem | I can search for relevant solutions | 1
1 | SB1/US2 | Developer | Understand user stories | I can search for dataset accordingly | 1
1 | SB1/US3 | User | Fill the application form | Applicant details will be saved | 1
1 | SB1/US4 | User | Set object to write | I can set the object | 1
1 | SB1/US5 | User | Change the object | I can change the writing object | 1
1 | SB1/US6 | User | Edit Form Details | I can change old details | 2
2 | SB2/US1 | User | Write on the screen without physical interaction | I can write on the screens | 2
2 | SB2/US2 | Developer | Trace the object user using to write | I can get the signature on the screen | 2
2 | SB2/US3 | Developer | Save the sign into databse | Signature will be saved in Database | 2
2 | SB2/US4 | User | Change my signature | Old sign will be replaced with new one | 3
2 | SB2/US5 | User | Delete my signature | My sign details will be deleted from the data | 3
2 | SB2/US6 | User | View my details | I can check my signature | 3
2 | SB2/US7 | User | Sign in front of webcam | I can put my signature for verification | 3
2 | SB2/US8 | User | Retry | I can try again if my previous signature is wrong | 3
3 | SB3/US1 | Developer | Find website for dataset | I can use it | 3
3 | SB3/US2 | Developer | Download datasets from various sources | I can train model on it | 3
3 | SB3/US3 | Developer | Normalize and stem my data | I can simplify my dataset | 3
3 | SB3/US4 | Developer | Train my data on different models | I can test it's accuracy and performance on each algorithm | 3
3 | SB3/US5 | Developer | Choose most accurate algorithm | I can implement that and get best results | 3
3 | SB3/US6 | Developer | Apply my trained model on user stories | Application can be used | 3
4 | SB4/US1 | DBA | Login into the System | I Can access the the System | 4
4 | SB4/US2 | DBA | Fire Update Queries(Modify Profile) | I Can update the Data | 4
4 | SB4/US3 | DBA | Check the Status of application form | I Can see the new application forms and validate | 4
4 | SB4/US4 | DBA | Change the status of applivcation form | I Can authenticate or deauthenticate the applications | 4
4 | SB4/US5 | DBA | View Applications | I Can check applicant's signature manually | 4
4 | SB4/US6 | DBA | Fire Update Queries | I Can Keep The Database Updated | 4
4 | SB4/US7 | DBA | Fire Delete Queries | I Can Remove Unwanted Data | 4
4 | SB4/US8 | DBA | Fire Select Queries | I Can See data that I want | 4
4 | SB4/US9 | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use | 4
4 | SB4/US10 | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More | 4
4 | SB4/US11 | DBA | View Application | I Can see Application Form | 4
4 | SB4/US12 | DBA | Download Application | I Can Download Application form | 4
4 | SB4/US13 | Developer | Create GUI for the project | Application can be deployed | 5

## SB1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Signature authentication in Air>
SB1/US1 | Understand the problem | SB1/D1/T1 | Breaking the problem and understanding each component | AS+AK+LC | STARTED
|  | SB1/D1/T2 | Searching for relavent solutions | AS+AK+LC | STARTED
|  | SB1/D1/T3 | Searching alternative approches | AS+AK+LC | STARTED
|  | SB1/D1/T4 | Analysing similar projects | AS+AK+LC | STARTED
SB1/US2 | Understand user stories | SB1/D2/T1 | Looking for various use cases | AS+AK+LC | STARTED
|  | SB1/D2/T2 | Discussion about user stories | AS+AK+LC | STARTED
|  | SB1/D2/T3 | Searching for type of data required | AS+AK+LC | STARTED
SB1/US3 | Fill the application form | SB1/D3/T1 | Create a web form | AK | NOT STARTED
|  | SB1/D3/T2 | Design database schema | AS+AK+LC | NOT STARTED
|  | SB1/D3/T3 | Create Databse | LC | NOT STARTED
SB1/US4 | Set object to write | SB1/D4/T1 | Study OpenCV and basic image processing | AS+AK+LC | NOT STARTED
|  | SB1/D4/T2 | Implement object tracking | AS+AK+LC | NOT STARTED
|  | SB1/D4/T3 | Modify object tracking according to the user stories | AS | NOT STARTED
SB1/US5 | Change the object | SB1/D5/T1 | Delete previous data | AS | NOT STARTED
|  | SB1/D5/T2 | Save new data of object | AS | NOT STARTED
SB1/US5 | Edit Form Details | SB1/D6/T1 | Edit user form details | AK+LC | NOT STARTED

## SB HOURS 1
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Fill the application form | Creating the Application form | AS+AK+LC
|  | Creating Database for Application form | AS+AK+LC
|  | Add Validations | AS+AK+LC
|  | Store the data of application form | AS+AK+LC
2 | Set device to write | Set the Webcam | AS+AK+LC
AS+AK+LC
3 | Change the device |  | AS+AK+LC
AS+AK+LC
4 | Set the constraints for writing device | Set the Color that Webcam will sence | AS+AK+LC
5 | Edit Details | Change the Data of Application form (Signature) | AS+AK+LC
|  | Save the data after Change | AS+AK+LC
| AS | Abhishek Sharma
| AK | Ankit Kumawat
| LC | Lokesh Choudhary
Verified By:
(Product Owner)

## SB BD 1
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 |  |  | Tasks
2018-09-11 |  | 2
2018-09-12
2018-09-14
2018-09-16
2018-09-18
Days

## SB2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Signature authentication in Air>
SB2/US1 | Write on the screen without physical interaction | SB2/D1/T1 | Open the Webcam | AS+AK+LC
|  | SB2/D1/T2 | Write front of the Camera | AS+AK+LC
|  | SB2/D1/T3 | Add Validations | AS+AK+LC
|  | SB2/D1/T4 | Store the data of application form | AS+AK+LC
SB2/US2 | Sign on the form | SB2/D2/T1 | Fill the Application Form | AS+AK+LC
|  | SB2/D2/T2 | Sign the on Application | AS+AK+LC
|  | SB2/D2/T3 | Save the DataAS+ | AS+AK+LC
SB3/US3 | Change my signature | SB2/D3/T1 | Edit the Signature | AS+AK+LC
|  | SB2/D3/T2 | Save the data after Change | AS+AK+LC
SB4/US4 | Delete my signature | SB2/D4/T1 | Delete the Signature | AS+AK+LC
SB5/US5 | View my details | SB2/D5/T1 | View Applications | AS+AK+LC
|  | SB2/D5/T2 | Open the Application
SB5/US6 | Sign in front of webcam | SB2/D5/T1 | Sign on the Webcam | AS+AK+LC
|  | SB2/D5/T2 | Save the data after Change | AS+AK+LC
SB5/US7 | Retry | SB2/D5/T1 |  | AS+AK+LC
|  | SB2/D5/T2 |  | AS+AK+LC

## SB HOURS 2
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Write on the screen without physical interaction | Open the Webcam | AS+AK+LC
|  | Write front of the Camera | AS+AK+LC
|  | Add Validations | AS+AK+LC
|  | Store the data of application form | AS+AK+LC
2 | Sign on the form | Fill the Application Form | AS+AK+LC
|  | Sign the on Application | AS+AK+LC
|  | Save the DataAS+ | AS+AK+LC
3 | Change my signature | Edit the Signature | AS+AK+LC
|  | Save the data after Change | AS+AK+LC
4 | Delete my signature | Delete the Signature | AS+AK+LC
5 | View my details | View Applications | AS+AK+LC
Open the Application
6 | Sign in front of webcam | Sign on the Webcam | AS+AK+LC
|  | Save the data after Change | AS+AK+LC
7 | Retry |  | AS+AK+LC
AS+AK+LC
| AS | Abhishek Sharma
| AK | Ankit Kumawat
| LC | Lokesh Choudhary
Verified By:
(Product Owner)

## SB BD 2
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 |  |  | Tasks
2018-09-11
2018-09-12
2018-09-14
2018-09-16
2018-09-18
Days

## SB3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Signature authentication in Air>
SB3/US1 | Login into the System | SB3/D1/T1 | Login by Username And Password | AS+AK+LC
|  | SB3/D1/T2 | View Application | AS+AK+LC
SB3/US2 | Fire Update Queries(Modify Profile) | SB3/D2/T1 | Click on Update Details | AS+AK+LC
|  | SB3/D2/T2 | Update the profile | AS+AK+LC
|  | SB3/D2/T3 | Save the data after Change | AS+AK+LC
SB3/US3 | Check the Status of application form | SB3/D3/T1 | Check the Status | AS+AK+LC
|  | SB3/D3/T2 | Check it is Updated or Not | AS+AK+LC
SB3/US4 | Change the status of applivcation form | SB3/D4/T1 | If Not Change the Update the Profile | AS+AK+LC
|  | SB3/D4/T2 | Save the Updated Profile | AS+AK+LC
SB3/US5 | View Applications | SB3/D5/T1 | View Application | AS+AK+LC
SB3/US6 | Fire Update Queries | SB3/D4/T1 | Click on Update Details | AS+AK+LC
|  | SB3/D4/T2 | Save the Data | AS+AK+LC
SB3/US7 | Fire Delete Queries | SB3/D4/T1 | Click on Delete Details | AS+AK+LC
|  | SB3/D4/T2 | Save the Data | AS+AK+LC

## SB HOURS 3
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Login into the System | Login by Username And Password | AS+AK+LC
|  | View Application | AS+AK+LC
2 | Fire Update Queries(Modify Profile) | Click on Update Details | AS+AK+LC
|  | Update the profile | AS+AK+LC
|  | Save the data after Change | AS+AK+LC
3 | Check the Status of application form | Check the Status | AS+AK+LC
|  | Check it is Updated or Not | AS+AK+LC
4 | Change the status of applivcation form | If Not Change the Update the Profile | AS+AK+LC
|  | Save the Updated Profile | AS+AK+LC
5 | View my details | View Application | AS+AK+LC
6 | Fire Update Queries | Click on Update Details | AS+AK+LC
|  | Save the data after Change | AS+AK+LC
7 | Fire Delete Queries | Click on Delete Details | AS+AK+LC
|  | Save the Data | AS+AK+LC
| AS | Abhishek Sharma
| AK | Ankit Kumawat
| LC | Lokesh Choudhary
Verified By:
(Product Owner)

## SB BD 3
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 |  |  | Tasks
2018-09-11
2018-09-12
2018-09-14
2018-09-16
2018-09-18
Days

## SB4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Signature authentication in Air>
SB4/US1 | Fire Select Queries | SB4/D1/T1 | To View selected data | AS+AK+LC
|  | SB4/D1/T2 |  | AS+AK+LC
|  | SB4/D1/T3 |  | AS+AK+LC
|  | SB4/D1/T4 |  | AS+AK+LC
SB4/US2 | Take Backup | SB4/D2/T1 | Backup of all Application forms | AS+AK+LC
|  | SB4/D2/T2 | Store that Data | AS+AK+LC
SB4/US3 | Delete Backup | SB4/D3/T1 | Delete Application from Backup Data | AS+AK+LC
|  | SB4/D3/T2 | Save the data | AS+AK+LC
SB4/US4 | View Application | SB4/D4/T1 | View the Application form | AS+AK+LC
SB4/US5 | Download Application | SB4/D5/T1 | Download the Application form in Computer | AS+AK+LC

## SB HOURS 4
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Fire Select Queries | To View selected data | AS+AK+LC
AS+AK+LC
AS+AK+LC
AS+AK+LC
2 | Take Backup | Backup of all Application forms | AS+AK+LC
|  | Store that Data | AS+AK+LC
3 | Delete Backup | Delete Application from Backup Data | AS+AK+LC
|  | Save the data | AS+AK+LC
4 | View Application | View the Application form | AS+AK+LC
5 | Download Application | Download the Application form in Computer | AS+AK+LC
| AS | Abhishek Sharma
| AK | Ankit Kumawat
| LC | Lokesh Choudhary
Verified By:
(Product Owner)

## SB BD 4
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 |  |  | Tasks
2018-09-11
2018-09-12
2018-09-14
2018-09-16
2018-09-18
Days

## BD
Date | Planned Task | Actual Uncompleted Task
2018-08-06 | 10 | 2
13 Aug. 2018 | 5 | 3
20 Aug. 2018 | 4 | 2
27 Aug. 2018 | 5 | 0
4 Sept. 2018 | 4 | 2
Total | 28 | 9